## Sheet1
Name of the Project - Uttarakhand Decentralized Watershed Development Project Phase-II (IDA Credit 5369-IN)
Proposed Annual Work Plan FY 2021-22 (Financial Target)
Rs. In Lakh
Activity Code | Project Component | April 21 to January 2022 | February & March 2022 | FY 2021-22 Total Financial Target (3+4) | IDA Contribution | Government Contribution | Beneficiary Contribution
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Social Mobilization and Participatory Watershed Planning
1.1 | Social Mobilization & Preparation of plan | 1942.7383 | 202.6006 | 2145.3389 | 860.9458 | 1284.393 | 0
1.2 | Preparation of GPWDP/MWS Plans | 0 | 0 | 0 | 0 | 0 | 0
| Total 1 (Social Mobilization & Participatory Watershed Planning) | 1942.7383 | 202.6006 | 2145.3389 | 860.9458 | 1284.393 | 0
2 | Watershed Treatment & Rainfed Area Development
2.1 | Watershed Treatment & Water Source Sustainability | 9325.3134 | 0 | 9325.3134 | 7460.2507 | 1398.797 | 466.2657
2.2 | Rainfed Area Development | 1673.5679 | 0 | 1673.5679 | 1338.8543 | 135.1806 | 199.533
| Total 2 (Watershed Treatment & Rainfed Area Development) | 10998.8813 | 0 | 10998.8813 | 8799.105 | 1533.9776 | 665.7987
3 | Enhancing Livelihood Opportunities
3.1 | Agri-business Support | 1738.5186 | 0 | 1738.5186 | 1390.8149 | 347.7037 | 0
3.2 | Support for Vulnerable Groups | 811.13 | 0 | 811.13 | 648.904 | 162.226 | 0
3.3 | Consolidation of Gramya I Activities | 30.7 | 0 | 30.7 | 24.56 | 6.14 | 0
| Total - 3 (Enhancing Livelihood Opportunities) | 2580.3486 | 0 | 2580.3486 | 2064.2789 | 516.0697 | 0
4 | Knowledge Management and Project Coordination
4.1 | Knowledge Management | 1269.7131 | 0 | 1269.7131 | 1015.7705 | 253.9426 | 0
4.2 | Project Coordination | 1572.0903 | 184.711 | 1756.8013 | 789.7343 | 967.067 | 0
| Total 4 (Knowledge Management and Project Coordination) | 2841.8035 | 184.711 | 3026.5145 | 1805.5048 | 1221.0096 | 0
| GRAND TOTAL | 18363.7717 | 387.3116 | 18751.0833 | 13529.8346 | 4555.45 | 665.7987
| Percentage against Grand Total |  |  | 100 | 73.6768 | 24.8067 | 3.6256

## Annual Work Calender2021-2022
Name of the Project - Uttarakhand Decentralized Watershed Development Project Phase-II (IDA Credit 5369-IN)
Proposed Annual Work Plan Calender FY 2021-22
Financial Rs. In Lakh
Activity Code | Project Component | Division | Unit | Unit Cost (INR Lakh) | Beneficiary Contribution in (%) | April 2021 to January 2022 |  | Progress Up to Sept.2021 |  | Proposed Target October.2021 |  | Proposed Target November.2021 |  | Proposed Target December.2021 |  | Proposed Target January.2022 |  | Februaru & March 2022 |  | F.Y. Total Target April 2021 to March 2022
[6 empty] | Physical Target | Financial Target | Physical Target | Financial Target | Physical Target | Financial Target | Physical Target | Financial Target | Physical Target | Financial Target | Physical Target | Financial Target | Physical Target | Financial Target | Physical Target | Financial Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Social Mobilization and Participatory Watershed Planning
1.1 | Social Mobilization & Preparation of plan
1.1.1 | Hiring of Partner NGOs |  | No. | LS | 0 | 1 | 37.81 | 1 | 19.5087 |  | 4.5753 |  | 4.5753 |  | 4.5753 |  | 4.5753 | 0 | 0 | 1 | 37.81
1.1.2`.1 | Hiring of Facilitating NGOs |  | No. | LS | 0 | 2 | 225 | 2 | 104.2557 |  | 30.1861 |  | 30.1861 |  | 30.1861 |  | 30.1861 | 0 | 0 | 2 | 225
1.1.2.2 | Hiring of Social Facilitator |  | per month | 0.16 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 154 | 26.04 | 154 | 26.04
1.1.3 | Hiring of village motivators | 287.1325 | per month | 0.025 | 0 | 11485 | 287.125 | 6139 | 119.7125 | 1069.2 | 33 | 1069.2 | 33 | 1069.2 | 35 | 2138.4 | 66.42 | 0 | 0 | 11485 | 287.125
1.1.4 | GPs administrative expenses | 362.789 | GP/year | 0.71 | 0 | 527 | 362.79 | 527 | 229.399 | 0 | 30 | 0 | 30 | 0 | 30 | 0 | 43.39 | 0 | 0 | 527 | 362.79
1.1.5 | Salary of Project Field Staff | [5 empty] | 866.556 |  | 436.5136 |  | 107.5106 |  | 107.5106 |  | 107.5106 |  | 107.5106 | 0 | 147.7176 | 0 | 1014.2737
1.1.6 | Office running expenses | [5 empty] | 163.4572 |  | 57.2348 |  | 26 |  | 26.5 |  | 26.5 |  | 27.2206 | 0 | 28.8429 | 0 | 192.3002
| Total 1 (Social Mobilization & Participatory Watershed Planning) | [5 empty] | 1942.7383 |  | 966.6243 |  | 231.272 |  | 231.772 |  | 233.772 |  | 279.3026 |  | 202.6006 |  | 2145.3389
2 | Watershed Treatment & Rainfed Area Development | [15 empty] | 0 |  |  | 0 | 0
2.1 | Watershed Treatment & Water Source Sustainability | [15 empty] | 0 |  |  | 0 | 0
[11 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
2.1.1 | GPWDP Plan | 8451.2548 | No. of GPWDP | LS | 5 | 527 | 8451.2504 | 527 | 3284.0048 |  | 1314.0884 |  | 1419.0605 |  | 1459.0605 |  | 975.0405 |  | 0 | 527 | 8451.2504
2.1.2 | MWS Plan ( Inter space GP) | 874.063 |  |  |  | 82 | 874.063 | 67 | 390.593 |  | 120.8675 |  | 120.8675 |  | 120.8675 |  | 120.8675 |  | 0 |  | 874.063
| Total 2.1(Watershed Treatment & Water Source Sustainability) | 9325.3178 |  |  |  |  | 9325.3134 | 594 | 3674.5978 | 0 | 1434.9559 | 0 | 1539.928 | 0 | 1579.928 | 0 | 1095.908 | 0 | 0 |  | 9325.3134
2.2 | Rainfed Area Development | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
2.2.1 | Agriculture & Horticulture demonstrations | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
2.2.1.01 | Demo. of High Yielding agric. crops (0.2 ha. For rainfed agriculture) | 118.1136 | No. | 0.0414 | 20 | 3361 | 118.11 | 2658 | 53.6723 | 0 | 15.7406 | 503 | 30 | 200 | 15.7406 |  | 2.96 | 0 | 0 | 3361 | 118.11
2.2.1.02 | Adoption support of High yielding agric. crops (0.06 ha for rainfed area) | 150.001 | farmer | 0.01 | 20 | 15000 | 150 | 5817 | 56.5619 | 4000 | 33.3595 | 5000 | 36.3595 | 183 | 23.72 |  | 0 | 0 | 0 | 15000 | 150
2.2.1.03 | Demonstration of high yielding vegetable crops (0.08ha. for irrigated area) | 43.352 | No. | 0.051 | 20 | 850 | 43.35 | 659 | 33.462 |  | 0 | 100 | 4.94 | 91 | 4.95 |  |  | 0 | 0 | 850 | 43.35
2.2.1.04 | Orchard Development (250 plant/ha.) | 174.04 | Ha. | 0.666 | 20 | 311 | 174.04 | 253.09 | 87.0119 |  | 10 |  | 0 | 30 | 33.5141 | 28 | 43.5141 | 0 | 0 | 311.09 | 174.04
2.2.1.05 | Orchard Cluster Development | 371.9392 | Ha. | 0.666 | 20 | 303 | 371.938 | 200 | 123.3592 | 0 | 0 | 13 | 28.58 | 40 | 100 | 50 | 120 | 0 | 0 | 303 | 371.938
2.2.1.06 | Polyhouses (100QM, 45QM & 27 QM.) | 197.6953 | No. | LS | 10 | LS | 197.6953 | 121 | 111.8816 | LS | 11.4534 | LS | 31.4534 | LS | 31.4534 | LS | 11.4534 | 0 | 0 | LS | 197.6953
2.2.1.07 | Poly tunnels | 28.6311 | 0.036 | 10 | 0 | 859 | 28.634 | 767 | 23.6434 |  |  | 59 | 3.74 | 33 | 1.2476 |  |  | 0 | 0 | 859 | 28.634
2.2.1.08 | Vermi compost Demonstration
2.2.1.08.1 | Vermi compost Demonstration | 35.632 | No. | 0.912 | 20 | 40 | 35.632 | 10 | 0.912 | 10 | 11.68 | 10 | 11.68 | 10 | 11.36 | 0 |  | 0 | 0 | 40 | 35.632
2.2.1.08.2 | Mother Vermi compost Demonstration | 37.3709 | No. | 0.912 | 20 | 431 | 37.37 | 130 | 8.5635 | 75 | 7.1691 | 75 | 7.3 | 76 | 7.1691 | 75 | 7.1691 | 0 | 0 | 431 | 37.37
2.2.1.09 | Improved agriculture/horticulture implements | 75.95 | LS | LS | 0 | LS | 75.95 | 0 | 66.2793 |  | 2.4177 |  | 2.4177 |  | 2.4177 |  | 2.4177 | 0 | 0 | LS | 75.95
| Total 2.2.1 (Agriculture & Horticulture Demonstration) | 1232.725 |  |  |  |  | 1232.7193 | 10615.09 | 565.3471 |  | 91.8204 |  | 156.4706 |  | 231.5726 |  | 187.5143 | 0 | 0 |  | 1232.7193
2.2.2 | Animal Husbandry Programme | [9 empty] | 0 |  | 0 |  | 0 |  | 0
2.2.2.01 | Livestock Improvement | [9 empty] | 0 |  | 0 |  | 0 |  | 0
2.2.2.01.01 | Natural Breeding Centres | [9 empty] | 0 |  | 0 |  | 0 |  | 0
2.2.2.01.01.01 | Natural Breeding Centres | 19.774 | No. | 1.653 | 5 | 13 | 19.774 | 10 | 9.3138 |  | 2.6151 | 3 | 7.8452 |  |  |  |  | 0 | 0 | 13 | 19.774
2.2.2.01.01.02 | Natural Breeding Centres Goat | 18.4502 | No. | 1.653 | 5 | 84 | 18.4549 | 30 | 11.1854 | 10 | 1.8174 | 20 | 3.64 | 20 | 1.8074 |  |  | 0 | 0 | 80 | 18.4549
2.2.2.01.02.1 | Mass A.I. | 1.28 | No. | LS | 0 | 0 | 1.28 | 0 | 0 |  |  |  | 1.28 |  |  |  |  | 0 | 0 | LS | 1.28
2.2.2.02 | Veterinary camps | 43.05 | No. | 0.375 | 0 | 122 | 43.05 | 36 | 24.978 | 22 | 4.593 | 22 | 4.593 | 22 | 4.593 | 20 | 4.293 | 0 | 0 | 122 | 43.05
2.2.2.03 | Stall feeding Program | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
2.2.2.03.01 | Animal shelter /sheds | 219.0196 | No. | 0.85 | 10 | 271 | 219.02 | 126 | 77.9586 | 36 | 34.9804 | 37 | 34.9804 | 36 | 36.12 | 36 | 34.9804 | 0 | 0 | 271 | 219.02
2.2.2.03.02 | Manger | 22.464 | No. | 0.096 | 10 | 234 | 22.464 | 113 | 4.0966 | 30 | 4.5919 | 30 | 4.5919 | 31 | 4.5919 | 30 | 4.5919 | 0 | 0 | 234 | 22.464
2.2.2.03.03 | Animal Chari | 28.182 | No. | 0.154 | 10 | 183 | 28.182 | 36 | 1.0866 | 37 | 6.7738 | 37 | 6.7738 | 37 | 6.7738 | 36 | 6.7738 | 0 | 0 | 183 | 28.182
| Total 2.2.2 (Animal Husbandry Programme) | 352.2198 |  |  |  |  | 352.2249 | 351 | 128.619 | 135 | 55.3715 | 149 | 63.7042 | 146 | 53.8861 | 122 | 50.6391 | 0 | 0 | 903 | 352.2249
2.2.3 | Fodder Production Programme | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
2.2.3.01 | Fodder Minikit | 20.9835 | N0. | 0.0067 | 20 | 3557 | 20.98 | 2325 | 12.2335 |  | 4.44 | 1232 | 4.31 |  | 0 |  | 0 | 0 | 0 | 3557 | 20.98
2.2.3.02 | Napier crop border plantation | 67.6351 | "000" mtrs | 0.182 | 20 | 455 | 67.636 | 395 | 32.8482 |  | 0 |  | 0 | 40 | 26.09 | 20 | 8.697 | 0 | 0 | 455 | 67.636
| Total 2.2.3 (Fodder Production Programme) | 88.6186 |  |  |  |  | 88.616 |  | 45.0817 | 0 | 4.44 |  | 4.31 |  | 26.09 |  | 8.697 | 0 | 0 |  | 88.616
| Total 2.2 (Rainfed Agriculture Development) | 1673.5633 |  |  |  |  | 1673.5602 |  | 739.0477 |  | 151.6318 |  | 224.4848 |  | 311.5486 |  | 246.8503 | 0 | 0 |  | 1673.5602
| Total 2 (Watershed Treat. & Rainfed Area Dvelo.) | 10998.8811 |  |  |  |  | 10998.8736 |  | 4413.6456 |  | 1586.5877 |  | 1764.4129 |  | 1891.4766 |  | 1342.7583 | 0 | 0 |  | 10998.8736
3 | Enhancing Livelihood Opportunities | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1 | Agri-business Support | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1.1 | Institution Building | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1.1.01 | ABSO Support (7 nos.) | 174.3722 | No. | LS | 0 | 7 | 174.37 | 7 | 23.5722 |  | 30 |  | 74.3 |  | 15.5 |  | 31 | 0 | 0 | 7 | 174.37
3.1.1.02 | Capacity Building Support | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
3.1.1.02.01 | Training at Unit level & division level | 58 | Trgs. No. | 1 | 0 | 66 | 58 | 20 | 10.7983 | 11 | 11.8004 | 12 | 11.8004 | 12 | 11.8004 | 11 | 11.8004 | 0 | 0 | 66 | 58
3.1.1.02.02 | Exposure visit - within state | 18.7 | Visits.No. | 0.85 | 0 | 22 | 18.7 | 6 | 2.535 | 4 | 4.0413 | 4 | 4.0413 | 4 | 4.0413 | 4 | 4.0413 | 0 | 0 | 22 | 18.7
3.1.1.02.03 | Exposure visit - outside state | 11.44 | Visits.No. | 1.43 | 0 | 8 | 11.44 | 1 | 1.416 | 1 | 1.506 | 2 | 3.006 | 2 | 3.006 | 2 | 2.506 | 0 | 0 | 8 | 11.44
3.1.2 | Input Support | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1.2.01 | High Value/High Yielding Agric,Horti. Crops | 643.93 | ha | LS | 0 | 901 | 643.93 | 466.97 | 363.521 | 100 | 69.8148 | 134 | 70.9648 | 100 | 69.8148 | 100 | 69.8148 | 0 | 0 | 900.97 | 643.93
3.1.2.02 | Post harvest support | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1.2.02.01 | Small civil works | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1.2.02.01.1 | Collection Centre | 29.48 | No. of Units | LS | 0 | 6 | 29.48 |  | 1.9935 | 2 | 8.3716 | 2 | 8.3716 |  | 8.3716 |  | 2.3716 | 0 | 0 | 4 | 29.48
3.1.2.02.01.2 | Growth Centre | 74.7578 | No. of Units | LS | 0 | 2 | 74.7578 |  | 14.6451 |  | 15.0282 |  | 15.0282 |  | 15.0282 |  | 15.0282 | 0 | 0 | 0 | 74.7578
3.1.2.02.02 | Goods | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.1.2.02.02.1 | Goods | 137 | LS | LS | 0 | LS | 137 |  | 75.0916 |  | 15.4771 |  | 15.4771 |  | 15.4771 |  | 15.4771 | 0 | 0 | LS | 137
3.1.2.02.02.2 | Goods For ABGC | 83.2 | LS | LS | 0 | LS | 83.2 |  | 3.7111 |  | 19.8722 |  | 19.8722 |  | 19.8722 |  | 19.8722 | 0 | 0 | LS | 83.2
3.1.2.02.03 | Other Support For ABGC | 38.3952 | LS | LS | 0 | LS | 38.4 |  | 7.3727 |  | 6.9081 |  | 6.9081 |  | 6.9081 |  | 10.2981 | 0 | 0 | LS | 38.4
3.1.2.03 | Pilot Fund Support | 469.2408 | LS | LS | 0 | LS | 469.24 |  | 71.2518 |  | 96.5273 |  | 100.4273 |  | 100.5173 |  | 100.5173 | 0 | 0 | LS | 469.24
| Total- 3.1 (Agribusiness Support) | 1738.516 |  |  |  |  | 1738.5178 |  | 575.9083 | 118 | 279.3469 | 154 | 330.1969 | 118 | 270.3369 | 117 | 282.7269 | 0 | 0 |  | 1738.5178
3.2 | Support for Vulnerable Groups | [9 empty] | 0 |  | 0 |  | 0 |  | 0
3.2.1 | Funds for Vulnerable Groups | [9 empty] | 0 |  | 0 |  | 0 |  | 0
3.2.1.01 | Individuals | 541.5 | No. | 0.3 | 0 | 1805 | 541.5 | 1113 | 328.129 | 180 | 53.3428 | 180 | 53.3428 | 180 | 53.3428 | 152 | 53.3428 | 0 | 0 | 1805 | 541.5
3.2.1.02 | Groups | 206 | No. | 1 | 0 | 206 | 206 | 93 | 92.82 | 28 | 28.295 | 28 | 28.295 | 29 | 28.295 | 28 | 28.295 | 0 | 0 | 206 | 206
3.2.2 | Funds for Transhumant | 63.63 | LS | LS | 0 |  | 63.63 |  | 41.2005 |  | 5.6074 |  | 5.6074 |  | 5.6074 |  | 5.6074 | 0 | 0 | 0 | 63.63
| Total - 3.2 (Support for Vulnerable Groups) | 811.13 |  |  |  |  | 811.13 |  | 462.1495 |  | 87.2451 |  | 87.2451 |  | 87.2451 |  | 87.2451 | 0 | 0 |  | 811.13
3.3 | Consolidation of Gramya I Activities | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3.3.1 | Training and Exposure | 7.7 | LS | LS | 0 | LS | 7.7 | 3 | 1.3243 |  | 1.5939 |  | 1.5939 |  | 1.5939 |  | 1.5939 | 0 | 0 | LS | 7.7
3.3.3 | Post Harvest Support /Pilot Support | 23 | LS | LS | 0 | LS | 23 |  | 8.2271 |  | 3.6932 |  | 3.6932 |  | 3.6932 |  | 3.6932 | 0 | 0 | LS | 23
| Total - 3.3 (Consolidation of Gramya I Activities) | 30.7 |  |  |  |  | 30.7 |  | 9.5513 | 0 | 5.2872 | 0 | 5.2872 | 0 | 5.2872 | 0 | 5.2872 | 0 | 0 | 0 | 30.7
| Total - 3 (Enhancing Livelihood Opportunities) | 2580.346 |  |  |  |  | 2580.3478 |  | 1047.6091 |  | 371.8792 |  | 422.7292 |  | 362.8692 |  | 375.2592 | 0 | 0 | 0 | 2580.3478
4 | Knowledge Management and Project Coordination | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0
4.1 | Knowledge Management | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0
4.1.1 | Capacity Building of Various Stakeholders | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0
4.1.1.01 | Training | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0
4.1.1.01.01 | Training at Village Level (one day 35 participant) | 53.119 | No.of Trgs. | 0.0878 | 0 | 605 | 53.119 | 269 | 17.0133 | 84 | 9.0264 | 84 | 9.0264 | 84 | 9.0264 | 84 | 9.0264 | 0 | 0 | 605 | 53.119
4.1.1.01.02 | Training at Division level (3-day trg 25 Participant) | 59 | No.of Trgs. | 1 | 0 | 59 | 59 | 38 | 25.0606 | 5 | 8.4849 | 6 | 8.4849 | 5 | 8.4849 | 5 | 8.4849 | 0 | 0 | 59 | 59
4.1.1.01.03 | Within state training | 15 | LS | LS | 0 |  | 15 | 6 | 2.8961 |  | 3.026 |  | 3.026 |  | 3.026 |  | 3.026 | 0 | 0 | 0 | 15
4.1.1.02 | Exposure visits | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
4.1.1.02.01 | Within State 3 days (25 Participants) | 29.65 | No. of Visits. | LS | 0 | LS | 29.65 | 12 | 3.0323 |  | 6.6544 |  | 6.6544 |  | 6.6544 |  | 6.6544 | 0 | 0 | 0 | 29.65
4.1.1.02.02 | Outside State 5 days (25 Participants) | 17.73 | No. of Visits. | LS | 0 | LS | 17.73 | 5 | 4.285 |  | 3.3613 |  | 3.3613 |  | 3.3613 |  | 3.3613 | 0 | 0 | 0 | 17.73
4.1.1.03 | Capacity Building of Staff | 0 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
4.1.1.03.01 | Training of staff | 16.6 | No. of Participant. | LS | 0 | LS | 16.6 | 8 | 4.5272 |  | 3.0182 |  | 3.0182 |  | 3.0182 |  | 3.0182 | 0 | 0 | 0 | 16.6
4.1.1.03.02 | Exposure visit of staff - outside state (15 Participants) | 17 | No. of Visits. | LS | 0 | LS | 17 | 2 | 0 |  | 4.25 |  | 4.25 |  | 4.25 |  | 4.25 | 0 | 0 | 0 | 17
4.1.1.03.03 | Exposure visit of staff - within state (15 Participants) | 16.7 | No. of Visits. | LS | 0 | LS | 16.7 | 0 | 1.5382 |  | 3.7904 |  | 3.7904 |  | 3.7904 |  | 3.7904 | 0 | 0 | 0 | 16.7
4.1.1.03.04 | Overseas Training | 0 | LS | LS | 0 | LS | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
| Sub Total | [7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
4.1.1.04 | Workshops | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
4.1.1.04.01 | National /State Level workshops | 6 | nos. | LS | 0 | 3 | 6 | 0 | 0 |  | 0 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 3 | 6
4.1.1.04.02 | WMD/PD level workshops /Project Staff | 9.5741 | events | 0.6 | 0 | 33 | 9.5741 | 8 | 1.1742 | 6 | 2.1 | 6 | 2.1 | 6 | 2.1 | 7 | 2.1 | 0 | 0 | 33 | 9.5741
4.1.1.04.03 | Division level workshops | 47.56 | Workshop No. | 0.58 | 0 | 82 | 47.56 | 44 | 7.7048 | 9 | 9.9638 | 10 | 9.9638 | 10 | 9.9638 | 9 | 9.9638 | 0 | 0 | 82 | 47.56
4.1.1.04.04 | Unit level workshops | 69.9667 | Workshop No. | 0.248 | 0 | 286 | 69.97 | 165 | 16.0029 | 30 | 13.7313 | 30 | 13.7313 | 31 | 13.5013 | 30 | 13 | 0 | 0 | 286 | 69.97
4.1.1.04.05 | Village level workshops | 104.784 | Workshop No. | 0.074 | 0 | 1416 | 104.784 | 726 | 33.2097 | 172 | 17.8936 | 173 | 17.8936 | 173 | 17.8936 | 172 | 17.8936 | 0 | 0 | 1416 | 104.784
4.1.1.04.06 | Special workshops at WMD/PD/DPD level | 46.3 | LS | LS | 0 | LS | 46.3 | 9 | 7.2562 |  | 9.7609 |  | 9.7609 |  | 9.7609 |  | 9.7609 | 0 | 0 | LS | 46.3
| Total 4.1.1 (Capacity Building of Various Stakeholders) | 508.9839 |  |  |  |  | 508.9871 |  | 123.7006 |  | 95.0611 |  | 97.0611 |  | 96.8311 |  | 96.3299 | 0 | 0 |  | 508.9871
4.1.2 | Centre of Excellence for Watershed Management | 47.98 |  |  |  |  | 47.98 |  | 0 |  | 11.995 |  | 11.995 |  | 11.995 |  | 11.995 | 0 | 0 | 0 | 47.98
4.1.3 | Information, Education and Communication. | 177.75 |  |  |  |  | 177.75 |  | 21.6296 |  | 39.0301 |  | 39.0301 |  | 39.0301 |  | 39.0301 | 0 | 0 | 0 | 177.75
4.1.4 | Monitoring, Evaluation and Learning | 535 |  |  |  |  | 535 |  | 0 |  | 133.75 |  | 133.75 |  | 133.75 |  | 133.75 | 0 | 0 | 0 | 535
| Total 4.1 ( Knowledge Management) | 1269.7139 |  |  |  |  | 1269.7171 | 0 | 145.3302 | 0 | 279.8362 | 0 | 281.8362 | 0 | 281.6062 | 0 | 281.105 | 0 | 0 | 0 | 1269.7171
4.2 | Project Coordination | 1572.0878 |  |  |  |  | 1572.09 |  | 732.7584 |  | 209.018 |  | 208.2105 |  | 213.8905 |  | 208.2105 | 0 | 184.711 | 0 | 1756.801
| Total 4 (Knowledge Management and Project Coordination ) | 2841.8017 |  |  |  |  | 2841.8071 | 0 | 878.0885 | 0 | 488.8542 | 0 | 490.0467 | 0 | 495.4967 | 0 | 489.3155 | 0 | 184.711 | 0 | 3026.5181
| GRAND TOTAL (1-4) | 18363.7718 |  |  |  |  | 18363.7668 | 0 | 7305.9675 | 0 | 2678.5932 | 0 | 2908.9608 | 0 | 2983.6146 | 0 | 2486.6356 | 0 | 387.3116 | 0 | 18751.0784